## Sheet1
Game: BubbleBobble |  | Reflection on Sprint Plan #1
Group: 15
User Story | Task | Assigned To | Estimated Effort | Actual effort per tast(hours) | Done | Notes
| UML | Wouter | medium | 3 | yes | Some problems with the software
| Responsiblity driven design | Eric | high | 4 | yes
| Level Parser | Matthijs | medium | 3 | yes | Done by Daan en Arjo
| Java Doc | Everyone | low | 3 | some | Some was done, not everything
| write tests | Everyone | medium | 4 | some | Testing had some obstacles, so it is delayed
| sound efffects | Matthijs | high | 2 | yes
| multiple lives | Daan | low | 1 | no | Other items had more priority
| start-end of level | Daan | medium | 1 | some | Infrastrucure is done, only more levels need to be made
| fix maven tools | Arjo | low | 0 | no | Not sure why tools dont work
Main Problems Encountered
Problem 1
Description: | The program we used to make the UML (argouml), was terrible. Files kept getting corrupted and having to start all over again.
Reaction: | Find another program to make the UML.
Problem 2
Description: | A lot of things were required which were not in the sprint plan, like refactoring and bug fixes which easily took 10 hours to fix. All in all, a lot of extra work came outside of the sprint plan, meaning that this was not a good indication of the work done per person.
Reaction: | See adjustments next sprint
Adjustments for the next Sprint Plan:
Better estimating what is required for the next iteration. Also, we'll aim to be done on thursday, to be able to fix the final problems on friday. This'll allow us to be more flexible with extra work and deliver a better product.